## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Londhe Pranali | 2025-02-19 | Error with extraction via API | S2 | Londhe Pranali | Bugs | Adhered to the bank policy and extraction documents | 2025-02-20 | Open | Require further investigation
2 | Londhe Pranali | 2025-02-22 | Error with OCR text extraction accuracy | S3 | Londhe Pranali | bugs | Adopted Pre-processing techniques | 2025-02-23 | Closed | Enhanced the accuarcy
3 | Londhe Pranali | 2025-02-25 | Error with llm model fine-tuning | S6 | Londhe Pranali | complexity | Utilized distilled versions for better performace | 2025-02-26 | Closed | Improved performance

## Sheet2
Logical
User Interface
Maintainability
Standards
Others